## Blad1
Assetlist
Probation Area |  | Asset name | Asset Code | Artist | Status | Opmerkingen | List of general items
| Client Cell | [5 empty] | Bed | Hadewij
|  | Client Room | 3D_ENV_CC_Room | Marc | In planning |  | Speaker | Marc
|  | Bed | 3D_ENV_GEN_Bed | Hadewij | Done |  | Chair | Quinten
|  | Pillow | 3D_ENV_CC_Pillow | Hadewij | Done |  | Keycard Slot | Marc
|  | Fireplace | 3D_ENV_GEN_Fireplace | Hadewij | In planning |  | Door | Lara
|  | Lounge chair | 3D_ENV_GEN_Chair | Quinten | Done |  | Desk | Quinten
|  | Lounge table | 3D_ENV_CC_Table | Lara | In planning |  | Fireplace | Hadewij
|  | Infuser | 3D_ENV_CC_Infuser | Lara | In planning |  | Staff key card | Marc
|  | Keycard slot | 3D_ENV_GEN_KeycardSlot | Marc | Done |  | Light
|  | Door | 3D_ENV_GEN_Door | Lara | Done |  | thresh can
|  | Toilet | 3D_ENV_CC_Toilet | Lara | Done |  | PC | Quinten
|  | Sink | 3D_ENV_CC_Sink | Lara | Done |  | Rack
|  | Shower cabin | 3D_ENV_CC_Shower cabin | Quinten | In planning | Shower cabin door and lid | Glass display
|  | Closet | 3D_ENV_CC_Closet | Marc | Done
|  | Test chair |  | Quinten | Done | General asset
|  | Test desk | 3D_ENV_GEN_Desk | Quinten | Done
|  | Speaker | 3D_ENV_GEN_Speaker | Marc | Done |  | Status
|  | Shape puzzle | 3D_ENV_CC_ShapePuzzle | Quinten | Done |  | Done
|  | Star shape | 3D_ITEM_CC_StarShape | Quinten | Done |  | In planning
|  | Round shape | 3D_ITEM_CC_RoundShape | Quinten | Done
|  | Square shape | 3D_ITEM_CC_SquareShape | Quinten | Done
|  | Puzzle 2 | 3D_ENV_CC_Puzzle2 | Quinten | Done
|  | Puzzle 3 | 3D_ENV_CC_Puzzle3 | Quinten | Done
|  | Portrait painting | 3D_ITEM_CC_PortraitPainting | Marc | Done
|  | Bathroom key | 3D_ITEM_CC_BathroomKey | Marc | In planning
|  | Studio key | 3D_ITEM_CC_StudioKey | Marc | In planning
|  | Staff key Card | 3D_ITEM_GEN_StaffKeyCard | Marc | Done
|  | Impassable door |  | Lara | In planning | General asset
|  | Studio chair |  | Quinten | In planning | General asset
|  | Studio desk |  | Quinten | In planning | General asset
|  | Studio equipment | 3D_ENV_CC_Studio equipment | Quinten | In planning
|  | Dark window | 3D_ENV_CC_Dark window | Marc | In planning
Canteen
|  | Canteen room | 3D_ENV_CANT_Room | Marc | In planning
|  | Buffet Table | 3D_ENV_CANT_BuffetTable | Marc | In planning
|  | Canteen chairs |  | Quinten | In planning | General asset
|  | Thrash can | 3D_ENV_GEN_ThrashCan | Lara | In planning
|  | Canteen tables |  | Lara | In planning | General asset
|  | Plates | 3D_ENV_CANT_Plates | Lara | In planning
|  | Food | 3D_ENV_CANT_Food | Hadewij | In planning
Recreation room
|  | Recreation room | 3D_ENV_REC_Room | Marc | In planning
|  | Chess | 3D_ENV_REC_Chess | Marc | In planning
|  | Pool table | 3D_ENV_REC_Pooltable | Marc | In planning | Pool ball etc inclused
|  | Dart bord | 3D_ENV_REC_DartBord | Marc | In planning | Plastic arrows
Biotope
|  | Biotope | 3D_ENV_BIO_Room | Hadewij | In planning
|  | Tree's | 3D_ENV_BIO_Tree | Hadewij | In planning
|  | Bushes | 3D_ENV_BIO_Bushes | Hadewij | In planning
|  | Flower's | 3D_ENV_BIO_Flower | Hadewij | In planning
|  | Stone's | 3D_ENV_BIO_Stone | Hadewij | In planning
Teaching room
|  | Teaching room | 3D_ENV_CLASS_Room | Marc | In planning
|  | Survey paper | 3D_ENV_CLASS_SurveyPaper | Marc | In planning
|  | Chair |  | Quinten | In planning | General asset
|  | Desk |  | Quinten | In planning | General asset
Storage
|  | Storage room | 3D_ENV_STOR_Room | Quinten | In planning
|  | Ladder | 3D_ENV_STOR_Ladder | Quinten | In planning
|  | Notebook of past client | 3D_ENV_ITEM_Notebook | Quinten | In planning
|  | Cardbord box | 3D_ENV_STOR_Box | Quinten | In planning
Solitary
|  | Solitary room | 3D_ENV_SOL_Room | Marc | In planning
Hallways
|  | Plant | 3D_ENV_HALL_Plant | Hadewij | In planning
|  | Light | 3D_ENV_GEN_Light | Marc | In planning
|  | Chairs |  | Quinten | In planning | General asset
|  | Room sign | 3D_ENV_HALL_RoomSigns | Hadewij | In planning
|  | Ventilation | 3D_ENV_HALL_Ventilation | Quinten | In planning
|  | Floor modulair piece | 3D_ENV_HALL_Floor | Marc | In planning | Texture for each area
|  | Ceiling modulair piece | 3D_ENV_HALL_Ceiling | Marc | In planning | Texture for each area
|  | Wall modulair piece | 3D_ENV_HALL_Wall | Marc | In planning | Texture for each area
Staff Area |  | Asset name | Asset code |  |  | Opmerkingen
Entrance
|  | Stair case | 3D_ENV_ENTR_Staircase
|  | Front desk | 3D_ENV_ENTR_FrontDesk
Staff room
|  | Staff room | 3D_ENV_STAFF_Room
|  | PC |  | Quinten | In planning | General asset
|  | Chair |  | Quinten | In planning | General asset
|  | Desk |  | Quinten | In planning | General asset
Kitchen
|  | Kitchen room | 3D_ENV_KITCH_Room
Infirmary
|  | Infirmary room | 3D_ENV_INF_Room
|  | Infirmary beds |  | Hadewij | In planning | General asset
|  | Curtains with rails | 3D_ENV_INF_Curtain/Rails
|  | Medical trolleys | 3D_ENV_INF_Trolleys
|  | Medicine cabinet | 3D_ENV_INF_Cabinet
|  | Infirmary desk |  | Quinten | In planning | General asset
|  | Infirmary chair |  | Quinten | In planning | General asset
Morgue
|  | Morgue room | 3D_ENV_MORG_Room
|  | Examination table | 3D_ENV_MORG_ExaminationTable
|  | Instruments | 3D_ENV_MORG_Instruments
|  | Corpse closets | 3D_ENV_MORG_CorpseClosets
|  | Corpse bed | 3D_ENV_MORG_CorpseBeds
|  | Rack | 3D_ENV_GEN_Rack
|  | Glass display | 3D_ENV_GEN_Glass display
|  | PC |  | Quinten | In planning | General asset
|  | Trashcan |  |  |  | General asset
|  | Transporter bed | 3D_ENV_MORG_TransporterBed
|  | Transporter rails straight | 3D_ENV_MORG_TransporterRailsStriaght
|  | Transporter rails curve | 3D_ENV_MORG_TransporterRailsCurve
|  | Hairdryer | 3D_ENV_MORG_Hairdryer
|  | Sodium bottle | 3D_ENV_ITEM_SodiumBottle
|  | Shower tile | 3D_ENV_MORG_ShowerTile
|  | Shower | 3D_ENV_MORG_Shower
|  | Hatch | 3D_ENV_MORG_Hatch
|  | Door display | 3D_ENV_MORG_DoorDisplay
|  | Morgue door | 3D_ENV_MORG_MorgueDoor
|  | Transporter control panel | 3D_ENV_MORG_TransporterControlPanel
|  | Power supply puzzle | 3D_ENV_MORG_PowerSupplyPuzzle
|  | Examination bed | 3D_ENV_MORG_ExaminationBed
|  | Robot arms | 3D_ENV_MORG_RobotArms
|  | Surgery Equipement | 3D_ENV_MORG_SurgeryEquipments
|  | Brains on sticks | 3D_ENV_MORG_BrainsOnSticks
|  | Locker doors | 3D_ENV_MORG_LockerDoors
Director's office
|  | Director room | 3D_ENV_OFF_Room
|  | Window | 3D_ENV_OFF_Window
|  | Curtain | 3D_ENV_OFF_Curtain
|  | Carpet | 3D_ENV_OFF_Carpet
|  | Lava lamp big | 3D_ENV_OFF_LavaLampBig
|  | Lava lamp small | 3D_ENV_OFF_LavaLampSmall
|  | Lever | 3D_ENV_OFF_Lever
|  | Class cover | 3D_ENV_OFF_ClassCover
|  | Closet |  | Marc | In planning | General asset
|  | Coat hanger | 3D_ENV_OFF_CoatHanger
|  | Ceiling fan | 3D_ENV_OFF_CeilingFan
|  | Directors keycard | 3D_ENV_OFF_DirectorsKeycard
|  | Neuroscience book | 3D_ENV_OFF_NeuroscienceBook
|  | Anastasia book | 3D_ENV_OFF_AnastasiaBook
|  | Lab coat | 3D_ENV_OFF_LabCoat
|  | Office Chair |  | Quinten | In planning | General asset
|  | Office Desk |  | Quinten |  | General asset
|  | PC | 3D_ENV_GEN_PC | Quinten | In planning
|  | Mic | 3D_ENV_OFF_Mic | Quinten | In planning
|  | Monitor | 3D_ENV_OFF_Monitor
Incinerator
|  | Incinerator room | 3D_ENV_INC_Room
|  | Client 3 headphones | 3D_ITEM_INC_Headphones
Lab Area |  | Asset Name | Asset Code |  |  | Opmerkingen
Laboratory
|  | Laboratory room | 3D_ENV_LAB_Room
|  | Toxic chemical set | 3D_ENV_LAB_ChemSet
A.I. room
|  | AI room | 3D_ENV_AI_room
Library
|  | Library room | 3D_ENV_LIB_Room
|  | Bookcase | 3D_ENV_LIB_Bookcase
Observatory
|  | Observatory room | 3D_ENV_OBS_Room
Other
| Assistant 1 picture | 3D_ENV_Picture
Characters | Asset name | Asset code | Artist | Status | Opmerkingen
| Female body | 3D_CHAR_FemaleBody | Victoria & Lara | In planning | Victoria sculpt. Lara doet de rest
| Male body | 3D_CHAR_MaleBody | Victoria & Lara | In planning
| Dokter | 3D_CHAR_Dokter | Victoria & Lara | In planning
| Assistant 1 | 3D_CHAR_Assistant1 | Victoria & Lara
| Assistant 2 | 3D_CHAR_Assistant2 | Victoria & Lara
| Client 1 | 3D_CHAR_Client1 | Victoria & Lara
| Client 2 | 3D_CHAR_Client2 | Victoria & Lara | In planning
| Client 3 | 3D_CHAR_Client3 | Victoria & Lara | In planning
| Client 4 | 3D_CHAR_Client4 | Victoria & Lara
| Client 5 | 3D_CHAR_Client5 | Victoria & Lara
| Client 6 | 3D_CHAR_Client6 | Victoria & Lara
| Client 7 | 3D_CHAR_Client7 | Victoria & Lara
Particles
| Fire | 3D_PART_Fire
| Shower | 3D_PART_Shower
| Sodium | 3D_PART_Sodium
| Lazer | 3D_PART_Lazer
Code |  | Asset name | Developer | Status | Opmerkingen
Player
|  | ExploreStats.cs | Jordi | Done
|  | ExploreController.cs | Jordi | Done
|  | Interact.cs | Jordi | In planning
|  | ConversationController.cs | Jordi | In planning
|  | ConversationEffects.cs | Jordi | In planning
|  | PuzzleController.cs | Jordi | In planning
|  | MenuController.cs | Jordi | In planning
|  | CameraBehaviour.cs | Jordi | In planning
System
|  | PlayMode.cs | Jordi | Done
|  | GameData.cs | Sascha | In planning
|  | DayController.cs | Jordi | In planning
|  | Settings.cs | Jordi | In planning
Puzzles
|  | RushHour | Alieke | In planning
|  | LaserMaze | Sascha | In planning
|  | SpotTheDiffrences | Renzo | In planning
|  | IconsPuzzle | Alieke | In planning
UI
|  | ConversationUI | Jordi | In planning
|  | MenuUI | Alieke | In planning
|  | PuzzleUI | Renzo | In planning
|  | ExploreUI | Jordi | In planning
|  | InventoryUI | Renzo | In planning
|  | MinimapController | Renzo | In planning

## Blad2
Planning | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 44 | Week 45 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51
Alieke | Week 38: Planning; Week 39: RushHour.cs; Week 40: IconsPuzzle.cs; Week 41: MenuUI
Assetlist
Jordi | Escape rooms | ExploreController.cs | ConversationController.cs | DayController.cs | MenuController.cs | PuzzleController.cs | ConversationEffects | ConversationUI | Settings.cs
| uml | CameraBehaviour.cs | Interact.cs |  |  |  |  | ExploreUI
Playmode.cs
ExploreStats.cs
Sascha | Week 38: Story; Week 39: LaserMaze.cs; Week 40: Level design - Hall Area 1; Week 41: Level design - Solitary; Week 42: Level design - Canteen; Week 44: Level design - Recreation room; Week 45: Level design - Canteen
| Dialoog |  |  | GameData.cs
Level design - Client Cell
Renzo | Week 38: Shader; Week 39: SpotTheDiffrences.cs; Week 40: MinimapController; Week 41: InventoryUI; Week 42: InventoryUI; Week 44: PuzzleUI
Marc | Week 38: 3D_ENV_GEN_KeycardSlot; Week 39: 3D_ENV_CC_Room; Week 40: 3D_ENV_SOL_Room; Week 41: 3D_ENV_CANT_Room; Week 42: 3D_ENV_REC_Room
| 3D_ENV_GEN_Speaker | 3D_ENV_CC_Dark window | 3D_ENV_REC_Chess | 3D_ENV_CANT_BuffetTable | 3D_ENV_CLASS_Room
| 3D_ITEM_CC_PortraitPainting | 3D_ENV_HALL_Floor | 3D_ENV_REC_Pooltable | 3D_ENV_REC_DartBord | 3D_ENV_CLASS_SurveyPaper
| 3D_ITEM_GEN_StaffKeyCard | 3D_ENV_HALL_Ceiling
| 3D_ENV_CC_Closet | 3D_ENV_HALL_Wall
| 3D_ITEM_CC_BathroomKey | 3D_ENV_GEN_Light
3D_ITEM_CC_StudioKey
Quinten | Week 38: 3D_ENV_GEN_Chair; Week 39: 3D_ENV_CC_Studio equipment; Week 40: 3D_ENV_OFF_Mic; Week 41: 3D_ENV_STOR_Room
| 3D_ENV_GEN_Desk | 3D_ENV_GEN_PC | 3D_ENV_HALL_Ventilation | 3D_ENV_STOR_Ladder
| 3D_ENV_CC_ShapePuzzle |  |  | 3D_ENV_ITEM_Notebook
| 3D_ITEM_CC_StarShape |  |  | 3D_ENV_STOR_Box
3D_ITEM_CC_RoundShape
3D_ITEM_CC_SquareShape
3D_ENV_CC_Puzzle2
3D_ENV_CC_Puzzle3
3D_ENV_CC_Shower cabin
Lara | Week 38: 3D_ENV_CC_Toilet; Week 39: 3D_ENV_CC_Table; Week 40: 3D_ENV_CC_Infuser; Week 41: 3D_ENV_GEN_ThrashCan; Week 42: 3D_ENV_CANT_Plates
| 3D_ENV_CC_Sink | 3D_CHAR_Client3 | 3D_CHAR_Client3 | 3D_CHAR_Client2 | 3D_CHAR_Client2
3D_ENV_GEN_Door
Victoria | Week 38: 3D_CHAR_Client3; Week 39: 3D_CHAR_FemaleBody; Week 40: 3D_CHAR_Client2; Week 41: 3D_CHAR_Dokter; Week 42: 3D_CHAR_Dokter
3D_CHAR_MaleBody
Hadewij | Week 38: 3D_ENV_GEN_Bed; Week 39: 3D_ENV_HALL_Plant; Week 40: 3D_ENV_BIO_Flower; Week 41: 3D_ENV_BIO_Room
| 3D_ENV_CC_Pillow | 3D_ENV_HALL_RoomSigns | 3D_ENV_BIO_Stone | 3D_ENV_BIO_Tree
| 3D_ENV_GEN_Fireplace |  |  | 3D_ENV_BIO_Bushes
3D_ENV_CANT_Food